## Tabelle1
Planning Resource Sheet
AMEISE Project
AMEISE username: |  |  |  | 4TUKE-02 | [31 empty] | Name 1:
[21 empty] | Effort Distribution: | [14 empty] | Martin Roshko
Simulation Date: | [10 empty] | Run Number: | [16 empty] | Effort |  | Project Duration | [5 empty] | Matriculation No. 1:
[21 empty] | Types of Effort |  |  |  |  | % |  | PM |  | months |  | days |  |  |  | s2418091709
Project Calculation: | [20 empty] | Management |  |  |  |  | 0% |  | 0 |  | 0 |  | 0
AFP: |  |  |  | 200 | [16 empty] | Specification |  |  |  |  | 13% |  | 3.4272 |  | 1.1268 |  | 34.2982 |  |  |  | Name 2:
LOC: |  |  |  | 9800 | [16 empty] | Design |  |  |  |  | 32% |  | 8.4362 |  | 2.7738 |  | 84.4264 |  |  |  | Yaroslav Melnychyn
Est. Proj. Duration: |  |  |  | 8.668 |  |  |  |  | Formula: |  |  | Basic COCOMO- organic | [8 empty] | Coding |  |  |  |  | 22.5% |  | 5.9317 |  | 1.9503 |  | 59.3623 |  |  |  | Matriculation No. 2:
Est. Avg. Developers: |  |  |  | 3.0414 |  |  |  |  | Formula: |  |  | Basic COCOMO- organic | [8 empty] | Testing |  |  |  |  | 7.5% |  | 1.9772 |  | 0.6501 |  | 19.7874 |  |  |  | s2418091824
Est. PersonMonths: |  |  |  | 26.3632 |  |  |  |  | Formula: |  |  | Basic COCOMO- organic | [8 empty] | Reviews |  |  |  |  | 11.25% |  | 2.9659 |  | 0.97515 |  | 29.6812
[21 empty] | Manuals |  |  |  |  | 13.75% |  | 3.6249 |  | 1.1919 |  | 36.277
Project Schedule: | [20 empty] | Total Effort |  |  |  |  | 100% |  | 26.3632 |  | 8.668 |  | 263.8326 | [8 empty] | Additional Information:
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
Customer |  |  |  | R | [5 empty] | R | [5 empty] | R | [16 empty] | R | [7 empty] | 4
Axel
Bernd | [29 empty] | MN | MN | MN | R | [7 empty] | 4
Christine | SP | SP | SP | R | C | SD | SD | SD | SD | R | C | MD | MD | MD | MD | R | C | CD | CD | CD | CD | CD | CD | CD | TA | TI | TM | TS | C | MN | MN | MN | R | C | [6 empty] | 34
Diana | [17 empty] | CD | CD | CD | CD | CD | CD | CD | TA | TI | TM | TS | [12 empty] | 11
Richard | SP | SP | SP |  | C | SD | SD | SD | SD |  | C | MD | MD | MD | MD |  | C | [23 empty] | 14
Stefanie
Thomas | SP | SP | SP | R | C | SD | SD | SD | SD | R | C | MD | MD | MD | MD | R | C | CD | CD | CD | CD | CD | CD | CD | TA | TI | TM | TS | C | MN | MN | MN | R | C | [6 empty] | 34
97
Cost Estimation: | [34 empty] | Abreviations (Artefacts/Tasks):
|  | Salary(h) |  |  |  |  | Weeks |  |  |  |  | Months |  |  |  |  | Working Hours | CD CD: Salary (total); TS TS: B | C | D | R | S | T |  | CD | … | Code
Axel |  | 40 |  |  |  |  | 5 |  |  |  |  | 1.1499 |  |  |  |  | 8 | CD CD: 8000; TS TS: B | C | D | R | S | T |  | MD | … | Module Design
Bernd |  | 40 |  |  |  |  | 12 |  |  |  |  | 2.7598 |  |  |  |  | 8 | CD CD: 19200; TS TS: B | C | D | R | S | T |  | MN | … | Manuals/Documentation
Christine |  | 45 |  |  |  |  | 20 |  |  |  |  | 4.5996 |  |  |  |  | 8 | CD CD: 36000; TS TS: B | C | D | R | S | T |  | SD | … | System Design
Diana |  | 40 |  |  |  |  | 11 |  |  |  |  | 2.5298 |  |  |  |  | 8 | CD CD: 17600; TS TS: B | C | D | R | S | T |  | SP | … | Specification
Richard |  | 50 |  |  |  |  | 6 |  |  |  |  | 1.3799 |  |  |  |  | 8 | CD CD: 12000; TS TS: B | C | D | R | S | T |  | C | … | Correcting (eg. CSP … Correct Specificaton)
Stefanie |  | 40 |  |  |  |  | 13 |  |  |  |  | 2.9897 |  |  |  |  | 8 | CD CD: 20800; TS TS: B | C | D | R | S | T |  | R | … | Review (eg. RSP … Review Specification)
Thomas |  | 45 |  |  |  |  | 26 |  |  |  |  | 5.9795 |  |  |  |  | 8 | CD CD: 46800; TS TS: B | C | D | R | S | T |  | TA | … | Acceptance Test
[29 empty] | C | D | R | S | T |  | TI | … | Integration Test | bar: TS TS
Additional Costs (which ones?): | [6 empty] | Project manager: 1500€ + 15€/h | [10 empty] | CD CD: 21300; TS TS: B | C | D | R | S | T |  | TM | … | Module Test
Total Project Costs: | [17 empty] | CD CD: 181700; TS TS: B | C | D | R | S | T |  | TS | … | System Test

## Tabelle2
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
Customer |  |  |  | R
Axel | [23 empty] | CD | CD |  | TS | TA | CD
Bernd |  |  | R |  |  |  |  | TI | TI | R | [6 empty] | MN | MN | MN | R | [5 empty] | R |  |  | MN | MN |  | MN
Christine | SP |  | R | [5 empty] | TS | TS | SD | SD | SD |  |  | CD | MN | MN | MN | MN | SD | SD | SD | [5 empty] | MN | MN | MN | MN | MN
Diana | SP |  |  |  | CD | CD | CD | CD | [5 empty] | CD | CD | CD | [7 empty] | CD | CD |  | TS | TM | CD
Richard | SP | SP |  |  | SD | CD | CD | CD |  |  | MD | MD | MD | [7 empty] | SD | SD | SD | [5 empty] | CD
Stefanie |  | SP | R | R |  |  |  | TA | TS | R | SD | SD | SD | [6 empty] | R | [5 empty] | R
Thomas |  | SP |  | C | CD | CD | CD | TI | TM | TM |  |  |  | CD | CD | CD | MN | MN | MN | MN | C | MD | MD | CD | CD |  | TS | TI | MN | MN | MN |  | MN
6/7/8/9
Week | 5 | 6 | 7 | 8 | 9 | 10 | 11
Customer
Axel
Bernd
Christine |  | SP | SP | SP | SP
Diana |  | SP | SP | SP | SP
Richard |  | SP | SP | SP | SP
Stefanie
Thomas
Week | 12 | 13 | 14 | 15 | 16 | 17 | 18
Customer
Axel
Bernd
Christine | SP | SP | SP | SP | SP
Diana | SP | SP | SP | SP | SP
Richard | SP | SP | SP | SP | SP
Stefanie
Thomas
Week | 19 | 20 | 21 | 22 | 23 | 24 | 25
Customer
Axel
Bernd | R
Christine | R
Diana | SP
Richard
Stefanie | R
Thomas
Week | 12 | 13 | 14 | 15 | 16 | 17 | 18
Customer
Axel
Bernd
Christine
Diana
Richard
Stefanie
Thomas
Week | 12 | 13 | 14 | 15 | 16 | 17 | 18
Customer
Axel
Bernd
Christine
Diana
Richard
Stefanie
Thomas